## Reframing
822 Gaines Reframing
Date | Contractor | Expense | Details | Paid by | Credit | GRG | 2x4x10
Exterior framing
2006-08-28 | Mark Construction Invoice 255 | 33767.74 | Reframing and roof | GRG |  | 33767.74
2006-09-17 | Mark Construction Invoice 311 | 2924 | soffits, Facia | GRG |  | 2924
Interior Framing
2006-09-07 | Menards 86734 08 2393 | 428.91 | Interior framing | JH | 428.91 |  | 100
2006-09-10 | Menards 84586 06 1963 | 30.01 | Interior framing | JH | 30.01
2006-09-17 | Menards 84624 06 5231 | 190.09 | Interior framing | JH | 190.09 |  | 34
1014/2006 | Lowes 25938 | 153.94 | Interior framing | JH | 153.94 |  | 30
2006-10-16 | Menards 3958 07 8709 | 57.52 | Interior framing | JH | 57.52
2006-10-16 | Home Depot 21110000229278 | 39.8 | Interior framing | JH | 39.8 |  | 12
2006-10-17 | Menards 19895 07 7286 | 113.19 | Interior framing | JH | 113.19 |  | 31
2006-10-18 | Lowes 67931 | 127.31 | Interior framing | JH | 127.31 |  | 18
2006-10-19 | Menards 68459 07 0335 | 195.22 | Interior framing | JH | 195.22 |  | 36
2006-10-22 | Menards 84630 03 7094 | 98.5 | Interior framing | JH | 98.5 |  | 25
2006-10-22 | Lowes 25185 | 39.53 | Interior framing nails | JH | 39.53
2006-10-23 | Menards 5482 05 0540 | 110.67 | Interior framing | JH | 110.67 |  | 30
2006-10-16 | Dan McDaniels | 729 | Rough in 2nd floor | GRG |  | 729
2006-10-22 | Dan McDaniels | 648 | Rough in 2nd floor | GRG |  | 648
2006-10-27 | Dan McDaniels | 216 | Rough in 1st floor | GRG |  | 216
2007-01-26 | Menards 74721 06 7043 | 123.44 | Interior framing | JH | 123.44
interior framing Totals |  | 3301.13 |  |  | 1708.13 | 1593 | 316

## Siding
822 Gaines Siding\Trim
Date | Contractor | Expense | Details | Paid by | Credit | GRG
2007-05-14 | Menards 73072088774 | 20.9 | Brackets | JH | 20.9
2007-06-19 | Menards 5482060643 | 29.92 | #30 Felt | JH | 29.92
2007-07-01 | Menards 22658103633 | 114.96 | Ext. cedar | JH | 114.96
2007-07-05 | Midwest | 214 | Ext. Window caps | GRG |  | 214
2007-07-18 | Menards 84674031089 | 168.97 | Ext. cedar | JH | 168.97
2007-07-23 | Menards 65459059054 | 66.57 | Ext. cedar | JH | 66.57
2007-07-26 | IDSCO 7128 | 917.52 | Cement board Siding | GRG |  | 917.52
2007-07-27 | Menards 27578099415 | 74.23 | Ext. cedar | JH | 74.23
2007-07-31 | Menards 18574060299 | 46.45 | Ext. cedar | JH | 46.45
2007-08-01 | Menards 17366609043 | 17.21 | Window trim | JH | 17.21
2007-08-06 | Menards 17366053437 | 43.72 | Ext. Cedar | JH | 43.72
2007-08-10 | Mark Construction invoice 312 | 1080 | Install rear cement board | GRG |  | 1080
2007-08-10 | True Value c67553 | 93.58 | Concrete, Aluminium, break | JH | 93.58
2007-09-06 | Menards 79195055890 | 18.21 | dripcap gloves | JH | 18.21
2007-09-21 | Hyperion Construction | 2866.08 | repair\replace siding and window casings | GRG |  | 2866.08
Totals | Siding\ Trim | 5772.32 |  |  | 694.72 | 5077.6
2008-04-09 | Midwest Architectural Sheet Metal | 1815.2 | Half round gutters | GRG |  | 1815.2
Totals | Gutters | 1815.2 |  |  |  | 1815.2

## Windows
822 Gaines Windows
Date | Contractor | Expense | Details | Paid by | JH | GRG
2007-02-20 | IDSCO | 4340.13 | Windows | GRG |  | 4340.13
2007-05-16 | True Value | 3.84 | Window | JH | 3.84
2007-05-21 | Menards | 32.82 | Window | JH | 32.82
2007-05-19 | Midwest | 474.92 | Kitchen Window | GRG |  | 474.92
2007-07-26 | IDSCO | 518.95 | 2nd floor front window | GRG |  | 518.95
2007-05-01 | Elmer Tuck | 250 | Window installation | GRG |  | 250
2007-08-17 | Midwest | 534.86 | window trim and door jamb | GRG |  | 534.86
2008-04-09 | Midwest | 1477 | bay windows | GRG |  | 1477
Totals |  | 7632.52 |  |  | 36.66 | 7595.86
| Midwest Estimate | 500 | bay storm windows
8132.52

## Painting
822 Gaines Painting
Date | Supplier | Exterior | Interior |  | Paid by | credit | GRG
2007-06-02 | Sherwin-Williams 1766 | 130.99 |  | Paint ext | JH | 130.99
2007-06-29 | Sherwin-Williams 3117 |  | 72.65 | Paint int | MM | 72.65
2007-07-03 | Sherwin-Williams 3333 | 116.7 |  | Paint ext | MM | 116.7
2007-07-03 | Home Depot | 6.36 |  | Supplies ext | MM | 6.36
2007-07-03 | Menards 97964066188 | 18.9 |  | Supplies ext | MM | 18.9
2007-07-05 | Sherwin-Williams 3413 |  | 72.65 | Paint Int | JH | 72.65
2007-07-23 | Sherwin-Williams 4239 | 71.73 |  | Paint ext | MM | 71.73
2007-07-31 | Sherwin-Williams 7585 | 59.96 |  | Paint ext | JH | 59.96
2007-08-01 | Menards 84723060832 |  | 15.31 | Supplies int | JH | 15.31
2007-08-02 | Sherwin-Williams 4696 |  | 72.23 | Paint Int | MM | 72.23
2007-08-28 | Sherwin-Williams 5933 | 59.96 |  | Paint ext | JH | 59.96
2007-09-07 | Lowes S0107JN1 | 64.29 |  | Paint ext | JH | 64.29
2007-09-12 | Sherwin-Williams 6723-9 | 105.65 |  | Paint ext | MM | 105.65
2007-09-14 | Menards 84712062778 | 44.61 |  | Paint ext | JH | 44.61
2007-09-18 | Sherwin-Williams 8321-9 | 296.66 |  | Paint ext | MM | 296.66
9/18//2007 | Menards 18574074394 | 37.38 |  | Supplies ext | MM | 37.38
2007-09-18 | AAA rents 02-007142-01 | 334.39 |  | Hoist | MM | 334.39
2007-09-19 | Sherwin-Williams 7115-7 | 22.84 |  | Paint ext | MM | 22.84
2007-09-21 | Scott Morrison painter | 620 |  | Painting Exterior |  |  | 620
2007-09-24 | AAA rents 02-007201-01 | 133.75 |  | Hoist | MM | 133.75
2007-09-27 | Scott Morrison painter | 340 |  | Painting Exterior |  |  | 340
2007-09-28 | Sherwin-Williams 7587-7 | 59.96 |  | Paint ext | MM | 59.96
2007-09-30 | Sherwin-Williams 7649-5 | 45.69 |  | Paint ext | JH | 45.69
2007-10-22 | Sherwin-Williams 8784-9 | 22.84 |  |  | MM | 22.84
2007-11-07 | Menards 70398 07 8511 |  | 14.64 | mineral spirts, brush | MM | 14.64
2007-11-13 | Menards 58526 08 0724 |  | 15.99 | Shellac staircase | MM | 15.99
2008-01-07 | Menards 84630073943 |  | 15.49 | stripper | MM | 15.49
2008-01-07 | Home Depot 21110000527705 |  | 7.93 | stain | MM | 7.93
2008-02-15 | Home Depot 21110005840467 |  | 9.62 | staining | MM | 9.62
2008-02-18 | Home Depot 21110005772413 |  | 13.43 | staining | MM | 13.43
2008-02-28 | Lowe S0107db1 121978 |  | 10.67 | brushes | MM | 10.67
2008-03-08 | Lowe S0107KF1 11887 |  | 38.36 | staircase varnish | JH | 38.36
2008-03-22 | Ready Strip |  | 44.9 | bay window stripping | JH | 44.9
2008-04-08 | Sherwin-Williams 5747-9 | 54.41 |  | Garage | JH | 54.41
2008-04-17 | Mautz | 15.8 |  | stain | MM | 15.8
2008-04-17 | Lowe S0107jk51174505 |  | 7.95 | brushes | MM | 7.95
2008-04-25 | True Value G78690 |  | 32.47 | Front parlor stain | MM | 32.47
2008-04-26 | Home Depot 21110005821764 |  | 24.17 | staining | MM | 24.17
2008-05-17 | Sherwin Williams 7397-1 | 113.18 |  | Pait garage plus | JH | 113.18
Paint Totals |  | 2776.05 | 468.46 | 3244.51 |  | 2284.51 | 960
|  | 3244.51 |  |  |  | 3244.51

## Mechanicals
822 Gaines Mechanicals Heating - Insulation - Electrical - Plumbing
Date | Contractor | Expense | Details | Paid by | Credit | GRG
2006-10-09 | Ideal Mechanical | 6341 | heat only AC $1,411 |  | 6341
2007-01-03 | Mid America | -252.5 | efficiency (furnace)rebate |  | -252.5
Heating total |  | 6088.5 |  |  | 6088.5
2007-05-21 | McCormick Insulation | 1493 | insulation with rebates |  | 1493
Electrical
2007-10-02 | Bruns Electric | 4500 | Completed 11/02/2007 |  | 4500
2008-05-24 | Menards 22658039472 | 149.71 | basement coverup | JH | 149.71
Electrical Total |  | 4649.71 |  |  | 4649.71
Plumbing
2007-11-08 | Ewert | 7000 | water heater to be installed |  | 7000
2007-11-18 | Ebay 22015839695 | 12.64 | 2 kitchen drains | JH | 12.64
2008-05-17 | Bryan Ewert | 500 | Install fixtures |  |  | 500
2008-05-22 | B&B Drain Tech | 169.06 | clean drain |  |  | 169.06
2008-05-22 | B&B Drain Tech | 42.8 | camera drain |  |  | 42.8
Plumbing Total |  | 7724.5 |  |  | 7012.64 | 711.86
Totals |  | 32329.92 |  |  | 30906.2

## Interior
822 Gaines Interior
Date | Contractor | Expense | Details | Paid by | Credit | GRG
DRYWALL
2007-11-01 | Quad Cities Homebuilders |  | Donation towards drywall | 500
2006-12-18 | KJE Construction |  | Estimate $7,000
2007-03-01 | KJE Construction | 2500 |  |  |  | 2500
2007-05-01 | KJE Construction | 2000 |  |  |  | 2000
2007-07-08 | Menards 18574 05 1873 | 60.31 | 8 sheets drt wall | JH | 60.31
2007-10-05 | Rob Brock Plastering | 2705 | Drywall to finish work left by KJE |  |  | 2705
2007-11-10 | Menards 3937 09 5016 | 12 | drywall basement stairs | JH | 12
2007-11-20 | Lowes 87093 | 231.24 | Hardibacker bathroom tile | JH | 231.24
2007-11-20 | Lowes s0107c01 1031540 | 38.97 | bathroom tile | JH | 38.97
2008-05-17 | Menard 90734041704 | 53.63 | bathroom ceiling | JH | 53.63
Drywall Totals |  | 7601.15 |  |  | 396.15 | 7205
FLOORING
2007-10-02 | Menards 18535 08 9150 | 189 | 15 Durock plus screws(see porch for receipt) | JH | 189
2007-10-03 | Menards 1942 03 9274 | 26.46 | floor cement (47.90 -21.44 return) | JH | 26.46
2007-10-19 | Menards 3958039382 | 53.86 | floor cement | JH | 53.86
2007-10-20 | Menards 73088039392 | 93.63 | 10 Durock(see Fixture receipt) | JH | 93.63
2007-10-22 | Menards 84712 08 0686 | 10.07 | Durrock screws (see fixture receipt) | JH | 10.7
2007-10-27 | Home Depot 2111 00004 72365 | 231.49 | Marble 2nd flr bathrooms | JH | 231.49
2007-11-02 | Home Depot 2111 00004 83628 | 620.93 | Granite for kitchen | JH | 620.93
2008-11-08 | Home Depot 2111 00004 26619 | 15 | granite grout (see MISC receipt) | JH | 15
2008-01-24 | Home Depot 2111 00010 16971 | 11.22 | marble grout | JH | 11.22
2008-03-16 | Menards 15225 08 3425 | 41.51 | Pine trim | JH | 41.51
2008-04-23 | Sams 96008238005 | 61.38 | Bamboo flooring | JH | 61.38
2008-04-24 | Sams 30558238002 | 920.63 | Bamboo flooring, hall, Dinning Rm | JH | 920.63
Floor Totals |  | 2275.18 |  |  | 2275.81
Finish Work
2007-12-21 | Salvage Treasures | 42.8 | header Master bedroom closet |  |  | 42.8
2008-01-05 | Menards 84603089793 | 43.45 | Pine trim | JH | 43.45
2008-01-07 | Menards 84630073944 | 80.88 | Pine trim (see porch receipt) | JH | 80.88
2008-01-09 | Menards 58825023180 | 49.52 | Pine trim (see porch receipt) | JH | 49.52
2008-01-11 | JMC Remodeling | 2375 | Install trim 2/17-12/20,1/2-1/4,1/7-/11 |  |  | 2375
2008-03-16 | Menards 15224083425 | 127.22 | Trim | JH | 127.22
2008-03-30 | Menards 20942063959 | 50 | Trim front parlor (see garage receipt) | JH | 50
2008-04-03 | Home depot 21110005798996 | 27.82 | Trim front parlor | JH | 27.82
2008-04-19 | Menards 84723059561 | 41.41 | Trim kitchen | JH | 41.41
2008-04-27 | Menards 84675068260 | 18.48 | Trim kitchen | JH | 18.48
2008-04-28 | Seiffert 50014495 | 24.25 | Trim kitchen | JH | 24.25
2008-05-01 | Menards 84723072963 | 59.17 | Trim kitchen | JH | 59.17
Finish totals |  | 2940 |  |  | 522.2 | 2417.8

## Staircase
822 Gaines Staircase
Date | Contractor | Expense | Details | Paid by | Credit | GRG
2007-07-05 | Menards 84712050525 | 101.97 | staircase wall | JH | 101.97
2007-07-09 | Menards 84721083696 | 34.2 |  | JH | 34.2
2007-07-13 | Menards 97948085499 | 50.12 |  | JH | 50.12
2007-07-18 | Seiffert | 10.28 | spindle screws | JH | 10.28
2007-07-18 | Menards 16577042971 | 14.94 |  | JH | 14.94
2007-08-16 | Menards 97948078225 | 25.04 |  | JH | 25.04
2007-07-19 | White Cap | 6.5 |  | JH | 6.5
2007-08-05 | Pete Lyons | 2425 | staircase installation | GRG |  | 2425
2007-08-06 | Bob O'hareESTIMATE | 600 | staircase parts | bob | 600
Totals |  | 3268.05 |  |  | 843.05 | 2425

## Porch
822 Gaines Porch\Bay\Shed
Date | Contractor | Expense | Details | Paid by | Credit | GRG
2007-05-15 | Home Depot | 31.61 | Porch posts | JH | 31.61
2007-06-10 | Menards 84674082248 | 44.04 | Shed | JH | 44.04
2007-09-12 | Hyperion Construction | 2500 | rebuild\roof (see invoice 1248 siding) | GRG |  | 2500
2007-10-02 | Menards 18535 08 9150 | 128.95 | porch bead board ceiling, nails, bay casings | JH | 128.95
11/102007 | Menards 3937 09 5016 | 115.83 | Sheathing, felt misc | JH | 115.83
2007-11-12 | Menards 18571 08 4639 | 6.64 | nails | JH | 6.64
2007-11-15 | Salvaged Treasures | 7.49 | Bay trim | JH | 7.49
2007-11-16 | Menards 58526 06 4218 | 46.29 | shed trim | JH | 46.29
2007-11-16 | Roofing Wholesale & Supply | 120.04 | roofing shingles | JH | 120.04
2007-11-16 | Menards 84675 07 3081 | 32.67 | shed roof trim, nails staircase shellac | JH | 32.67
2007-12-08 | Salvaged Treasures | 16.05 | Bay trim | JH | 16.05
2008-01-07 | Menards 84630073944 | 154.82 | fir flooring | JH | 154.82
2008-01-09 | Menards 58825023180 | 186.21 | fir flooring | JH | 186.21
2008-04-17 | Menards 84675075746 | 84.78 | back Porch | JH | 84.78
2008-04-27 | Menards 57448070954 | 75.45 | front porch | JH | 75.45
2008-05-16 | Mark Construction Invoice 344 | 800 | porch stairs\ shed(see garage invoice) | GRG |  | 800
2008-05-18 | Menards 112071864 | 60 | door trim, back deck trim | MM | 60
2008-05-23 | Menards 57488074073 | 141.55 | porch steps ,screws | JH | 141.55
2008-05-25 | Menards 57412062945 | 85.49 | porch steps ,screws | JH | 85.49
2008-05-27 | Menards 57436064356 | 22.07 | porch screws,door lock | JH | 22.07
Totals |  | 4659.98 |  |  | 1359.98 | 3300
Basement stairs,windows, doors
Date | Contractor | Expense | Details | Paid by | Credit | GRG
2008-05-16 | Mark Construction Invoice 344 | 538.95 | porch stairs\ shed(see garage invoice) | GRG |  | 538.95
Totals |  | 538.95 |  |  | 0 | 538.95

## Garage
822 Gaines Garage
Date | Contractor | Expense | Details | Paid by | Credit | GRG
2008-03-30 | Menards 20942063959 | 110.49 | plywood for roof | JH | 110.49
2008-04-03 | Menards 73088079174 | 51.8 | scoffets | JH | 51.8
2008-04-03 | Menards 73088079174 | 161.71 | siding | JH | 161.71
2008-05-03 | Menards 757436061030 | 1065.01 | Garage door | JH | 1065.01
2008-05-16 | Mark Construction Invoice 344 | 5000 | Rebuild garage | GRG |  | 5000
Totals |  | 6389.01 |  |  | 1389.01 | 5000

## Hauling
822 Gaines Hauling Costs
Date | Contractor | Expense | Details | Paid by | Credit | GRG
2006-04-23 | Rush Roolloff estimate | 100 | per phone call 11/15/07 | rush | 100
2006-04-23 | Scott Landfill | 99 |  | sc | 99
2006-06-13 | Rush Roolloff estimate | 100 |  | rush | 100
2006-06-13 | Scott Landfill | 247.5 |  | sc | 247.5
2006-07-10 | Rush Roolloff estimate | 100 |  | rush | 100
2006-07-10 | Scott Landfill | 247.5 |  | sc | 247.5
2006-07-29 | Rush Roolloff estimate | 100 | All wood | rush | 100
2008-04-15 | Rush Roolloff estimate | 350 |  | rush | 350
Totals |  | 1344 |  |  | 1344 | 0

## Misc Costs
822 Gaines Miscellaneous costs
Date | Contractor | Expense | Details | Paid by | Credit | GRG
2006-03-28 | BLD -000349DAV | 55.55 | building permit | JH |  | 55.55
2006-04-11 | Menards 306310106083068 | 44.09 | 822 demolition | JH | 44.09
2006-04-13 | Menards 306310306068217 | 62.98 | 822 demolition | JH |  | 62.98
2006-06-19 | BLD -000978DAV | 187.55 | building permit | JH |  | 187.55
2006-10-10 | Menards 74721 05 3124 | 83.29 | outside covering | JH | 83.29
2007-09-20 | Menards 58526 05 1546 | 6.72 | metal primer | MM | 6.72
2007-09-20 | E&J Metal Co | 19.26 | brass for pcket doors | JH | 19.26
2007-11-03 | home depot 2111 00012 54895 | 2.11 | Electrical box | JH | 2.11
2007-11-05 | home depot 2111 00012 58169 | 29.3 | Electrical, patch | JH | 29.3
2007-11-05 | Menards 57448 06 8401 | 22.58 | bulbs\steel wool | MM | 22.58
2007-11-08 | Diamond Vogel | 9.68 | staircase stain | JH | 9.68
2007-11-08 | Menards 84691 06 0248 | 42.74 | stove cord, light bulbs, screws | JH | 42.74
2007-11-08 | home depot 2111 00059 43121 | 7.39 | steel wool | MM | 7.39
2007-11-07 | Big Lots | 48.66 | Drapes | MM | 48.66
2007-11-07 | Big Lots | 14.43 | Drapes | MM | 14.43
2007-11-12 | Big Lots | 8.56 | Drapes | MM | 8.56
2007-11-29 | Menards 58545 10 997801 | 67.64 | matts, hoses, stops,chaulking, gloves | JH | 67.64
2007-12-17 | Lowes S0107RD1 1006271 | 32.61 | Keys sealer, trim tiles | JH | 32.61
2007-12-27 | Chick gift for pocket door bushings | 40 |  | JH | 40
2008-11-08 | Home Depot 2111 00004 26619 | 20.8 | Bulbs | JH | 20.8
2008-01-09 | Menards 58825023180 | 23.19 | Bulbs sockets (see porch receipt) | JH | 23.19
2008-01-11 | Menards 27578066508 | 11.11 | Bulb, sockets | JH | 11.11
2008-04-28 | Salvation army | 10 | switch plates | JH | 10
2008-05-09 | Menards 20942057840 | 6.41 |  | JH | 6.41
2008-05-09 | Menards 90734062399 | 3.51 | screws | JH | 3.51
Sub Totals |  | 860.16 |  |  | 554.08 | 306.08
2006-11-06 | IA-IL Termite & Pest Control | 312 | Spray dry riot |  | 312
TAXES
2006-09-28 | Scott County 033512 | 114 |  |  |  | 114
2007-05-07 | Scott County 00258616 | 121 |  | JH | 121
tax sub total |  | 235 |  |  | 121 | 114

## Utilities
822 Gaines Utilities
Date | Contractor | Expense | Details | Paid by | Credit | GRG
2006-06-14 | Mid America | 9.1 | Electric |  |  | 9.1
2006-07-01 | Mid America | 126.48 |  |  |  | 126.48
822/2006 | Mid America | 24.06 |  |  |  | 24.06
2006-09-12 | Mid America | 26.49 |  |  |  | 26.49
2006-09-26 | Mid America | 73.81 |  |  |  | 73.81
2006-10-20 | Mid America | 45.3 |  |  |  | 45.3
2006-11-17 | Mid America | 28.47 |  |  |  | 28.47
2006-12-21 | Mid America | 20.46 |  |  |  | 20.46
2007-01-23 | Mid America | 17.02 |  |  |  | 17.02
2007-02-22 | Mid America | 17.82 |  |  |  | 17.82
2007-03-22 | Mid America | 18.52 |  |  |  | 18.52
2007-04-23 | Mid America | 19.4 |  |  |  | 19.4
2007-05-21 | Mid America | 16.59 |  |  |  | 16.59
2007-06-21 | Mid America | 16.68 |  |  |  | 16.68
2007-07-20 | Mid America | 22.38 |  |  |  | 22.38
2007-08-20 | Mid America | 40.19 |  |  |  | 40.19
2007-09-20 | Mid America | 43.9 |  |  |  | 43.9
2007-10-19 | Mid America | 27.58 |  |  |  | 27.58
2007-11-16 | Mid America | 63.08 |  |  |  | 63.08
2007-12-20 | Mid America | 240.28 |  |  |  | 240.28
2008-01-25 | Mid America | 282.02 |  |  |  | 282.02
2008-02-22 | Mid America | 256.36 | missing statement |  |  | 256.36
2008-03-24 | Mid America | 121.87 |  |  |  | 121.87
2008-04-22 | Mid America | 71.98 |  |  |  | 71.98
2008-05-22 | Mid America | 80.67 |  |  |  | 80.67
2006-11-15 | Iowa American Water | 162.5 | Water |  |  | 162.5
2007-02-14 | Iowa American Water | 74.72 |  |  |  | 74.72
2007-05-16 | Iowa American Water | 74.72 |  |  |  | 74.72
2007-07-31 | Iowa American Water |  | -197.29
2007-10-19 | Iowa American Water |  | -174.49
2007-10-19 | Iowa American Water | -125.65 |  |  |  | -125.65
2006-09-28 | Davenport S3144818 | 42.41 | Sewer | JH Chk 4112 | 42.41
2006-12-22 | Davenport S3188399 | 43.11 | Sewer | JH Chk 4117 | 43.11
2008-01-16 | Davenport S3404076 | -4.8 |  |  |  | -4.8
Totals |  | 1977.52 |  |  | 85.52 | 1892
1977.52

## App cab fixtures
822 Appliances Cabinets Fixtures
Date | Contractor | Expense | Details | Paid by | Credit | GRG
Appliance
2006-10-26 | Menards 73088 04 9927 | 177.96 | Bathroom fans | JH | 177.96
2006-12-05 | Menards 22658 07 2145 | 34.1 | bath vents | JH | 34.1
Appliance Totals |  | 212.06 |  |  | 212.06 | 0
Cabinets
2007-09-04 | Kitchen Bath Design | 1444.5 | Kitchen Cabinets\sink\counter |  |  | 1444.5
2007-11-10 | Menards 3937 09 5016 | 46 | Birch plywood (see porch receipt) | JH | 46
Cabinet Totals |  | 1490.5 |  |  | 46 | 1444.5
Fixtures
2007-10-20 | Menards 73088 03 9392 | 102.59 | toilet tank and parts | JH | 102.59
2007-10-20 | Menards 73088 03 9393 | 64.2 | toilet bowl | JH | 64.2
2007-10-22 | Menards 86719 60 1296 | -6.42 | tank sale refund | JH | -6.42
2007-10-22 | Menards 86719 60 1297 | -8.56 | bowl sale refund | JH | -8.56
2007-10-22 | Menards 84712 08 0686 | 345.38 | 2 toilets, ped sink accessories | JH | 345.38
2007-10-24 | Menards 3937 22 9254 | -8.57 | swap toilet for space saver | JH | -8.57
2007-11-03 | Home Depot 2111 00012 54887 | 683.52 | 2 bath sinks, kitchen light fixtures | JH | 683.52
2007-11-07 | Home Depot 2111 00004 96380 | 147.66 | 2 ceiling lights | MM | 147.66
2007-11-07 | Menards 15225 05 1320 | 284.59 | 5 ceiling lights | MM | 284.59
2007-11-10 | Menards 15225 08 9487 | 604.9 | Mirrored closet doors, shower door | JH | 604.9
2007-11-15 | Faucet discounters (EBay) | 285 | Kitchen, 3 bathroom faucets | JH | 285
2008-01-26 | Aldi Foods 30210015/003/148 | 128.37 | 3 Bathroom light set | MM | 128.37
2008-04-23 | Lowes S0107JS1 1153951 | 44.96 | Porch lights | JH | 44.96
2008-05-16 | Menards 90738081430 | 217.96 | upstairs hall and bedroom fans | MM | 217.96
2008-05-18 | Menards 112071864 | 36.64 | bathroom lite plus(see porch receipt) | MM | 36.64
Fixture Totals |  | 2922.22 |  |  | 2922.22 | 0

## QC Loan
822 Gaines Quad Cities Housing Cluster Loan
| Amount | monthly interest | current interest due | 2008-05-31 06:39
QC housing cluster loan 5.5% | 30000 | 137.5 | 3210.8417
2006-06-21

## ARS
Architectural Rescue Shop
Date | QTY | Item | Source | Value
| 1 | 6' clear fir 5 panel pocket door, trim and rail | Salvaged St. Ambroise 2116 Harrison c1890 | 500
| 1 | 6' clear fir 5 panel pocket door, trim and rail | Salvaged St. Ambroise 2116 Harrison c1890 | 500
| 1 | pair 3' clear fir 5 panel pocket door, trim and rail | Salvaged St. Ambroise 2116 Harrison c1890 | 500
| 1 | 3' 6" fir beveled glass top pocket door, trim and rail | Salvaged St. Ambroise 2116 Harrison c1890 | 300
| 1 | 4' leaded glass window | Salvaged St. Ambroise 2118 Harrison c1890 | 200
| 1 | 8' leaded glass window | Salvage c1900 | 600
| 17 | oak stair treads and risers | Salvage E18th St houses c1920 | 340
| 1 | oak staircase railings, spindles, posts | Salvaged Dennis Laroque, c1880 apartment house | 500
| 7 | Pine 30" 4 panel doors, jambs and trim | Salvaged E18th St | 350
| 1 | 2' x 3' 3 panel pine door for attic | Salvaged St Ambrose | 40
| 1 | Pine 26" 5 panel door, jamb and trim | Salvaged St Ambrose | 60
| 2 | Pine 30" 5 panel door, jamb and trim | Salvaged St Ambrose | 120
| 1 | Pine 32" 5 panel door, jamb and trim | Salvaged St Ambrose | 70
| 1 | 36" x 8' 4" front door\pine trim | Salvage JonWilson c 1870s | 120
| 1 | 36" back door\pine trim | Salvaged Mark Forester c1890s | 100
| 300' | Pine base board | Salvaged | 300
| 11 | Pine window header, sill and trim | Salvaged | 440
| 3 | Oak window header, sill and trim | Salvaged | 150
| 1 | Oak 4' door header and trim | Salvaged | 50
| 1 | 8' oak header and trim | Salvaged | 100
| 50' | oak base board | Salvaged | 75
| 7 | oval brass door knob sets | Salvaged E18th St | 210
| 1 | round attic window and trim | Salvaged | 200
| 1 | dish washer and stove | donation | 100
| 42 | porch spindles and rails | Salvaged Peterson VanMaur Dept store c 1890 | 500
6425

## Total Costs
| 822 Gaines Costs |  |  |  | May 31,2008
Project | Original Estimates | 2006 Estimates | April. 2008 Estimates | Optional | Actual to date | Over\under estimate | Paid by GRG | Donation | Credit | Tax credit
Reframing Mark Construction | 20000 | 23000 | 22767.74 |  | 22767.74 | 0 | 22767.74 |  |  | 22767.74
Roofing-Mark Construction | 11000 | 11000 | 11000 |  | 11000 | 0 | 11000 |  |  | 11000
Soffits Mark Construction |  | 3000 | 2924 |  | 2924 | 0 | 2924 |  |  | 2924
Interior framing |  | 3000 | 3301 |  | 3301.13 | 0.13 | 1593 |  | 1708.13 | 3301.13
Siding\Trim |  | 3000 | 5772 |  | 5772.32 | 0.32 | 5077.6 |  | 694.72 | 5772.32
Gutters |  | 600 | 1815 |  | 1815.2 | 0.2 | 1815.2 |  |  | 1815.2
Windows | 5000 | 5500 | 8000 |  | 7632.52 | -367.48 | 7595.86 |  | 36.66 | 7632.52
Painting | 5000 | 5000 | 3000 |  | 3244.51 | 244.51 | 960 |  | 2284.51 | 3244.51
Mechanicals | [9 empty] | 0
Heating \Air | 10000 | 7800 | 7800 |  | 6088.5 | -1711.5 |  |  | 6088.5 | 6088.5
Insulation | 2600 | 2600 | 1493 |  | 1493 | 0 |  |  | 1493 | 1493
Plumbing | 6700 | 6700 | 7200 |  | 7724.5 | 524.5 | 711.86 |  | 7012.64 | 7724.5
Electrical | 5000 | 5000 | 4500 |  | 4649.71 | 149.71 |  |  | 4649.71 | 4649.71
Interior | [9 empty] | 0
Drywall | 7000 | 7000 | 7700 |  | 7601.15 | -98.85 | 7205 | 500 | 396.15 | 7601.15
Flooring | 5000 | 5000 | 5000 |  | 2275.18 | -2724.82 |  |  | 2275.81 | 2275.18
Interior Finish work |  | 2000 | 3000 |  | 2940 | -60 | 2417.8 |  | 522.2 | 2940
Appliances\Cabinets\Fixtures | 5000 | 5000 | [7 empty] | 0
Appliances |  |  | 300 |  | 212.06 | -87.94 |  |  | 212.06 | 212.06
Cabinets |  |  | 1600 |  | 1490.5 | -109.5 | 1444.5 |  | 46 | 1490.5
Fixtures |  |  | 2800 |  | 2922.22 | 122.22 |  |  | 2922.22 | 2922.22
Garage Repair | 3000 | 6000 | 6000 |  | 6389.01 | 389.01 | 5000 |  | 1389.01 | 6389.01
Staircase |  | 3000 | 3328 |  | 3268.05 | -59.95 | 2425 |  | 843.05 | 3268.05
Porch \bay roof \shed |  | 2500 | 4500 |  | 4659.98 | 159.98 |  |  | 4659.98 | 4659.98
Basement door and windows |  | 1000 | 1000 |  | 538.95 | -461.05 | 538.95 |  | 0 | 538.95
Hauling |  | 800 | 1200 |  | 1344 | 144 |  |  | 1344 | 1344
Landscaping |  | 1000 | 1000 | 1000 |  | -1000 |  |  |  | 0
Miscellaneous costs |  |  | 1000 |  | 860.16 | -139.84 | 306.08 |  | 554.08 | 860.16
Tim-Bor pressure spray |  | 312 | 312 |  | 312 | 0 |  |  | 312 | 312
Taxes |  | 235 | 235 |  | 235 | 0 | 121 |  | 114
Utilities\hookup |  | 1000 | 2300 |  | 1977.52 | -322.48 | 1892 |  | 85.52 | 1977.52
General Contractor GRG | 8000 | 8000 | 2000 | 2000 |  | -2000 |  |  |  | 0
ARS Hardware, trim, doors, etc | 4000 | 4000 | 6425 |  | 6425 | 0 |  |  | 6425 | 6425
Selling Costs | 2100 | 2400 | 2700 | 2700 |  | -2700 |  |  |  | 0
Legal Fees | 1000 | 1000 | 1000 |  |  | -1000 |  |  |  | 0
Interest QCHC Loan |  | 2400 | 3300 |  | 3210.8417 | -89.1583 |  |  | 3210.8417
Insurance |  | 600 | 800 |  | 800 | 0 | 800
0
Totals | 100400 | 129447 | 137072.74 | 5700 | 125874.7517 | -11197.9883 | 76595.59 | 500 | 49279.7917 | 121628.91
[8 empty] | Contractors | 24710.6917
| Tax credit total = |  | 121628.91 | x 25% = | 30407.2275 |  |  | others | 24569.1
|  |  |  | Check | -0.63 | 499.37
|  | Sale price | 101372.74 | 131372.74 | 125375.3817 | 137072.74

## Summary
| 822 Gaines Costs |  |  |  | May 31,2008
Project | Original Estimates | 2006 Estimates | April. 2008 Estimates | Optional ? Expenses | Actual to date | Over\under estimates
Reframing Mark Construction | 20000 | 23000 | 22767.74 |  | 22767.74 | 0
Roofing- Mark Construction | 11000 | 11000 | 11000 |  | 11000 | 0
Soffits Mark Construction |  | 3000 | 2924 |  | 2924 | 0
Interior framing |  | 3000 | 3301 |  | 3301.13 | 0.13
Siding |  | 3000 | 5772 |  | 5772.32 | 0.32
Gutters |  | 600 | 1815 |  | 1815.2 | 0.2
Windows | 5000 | 5500 | 8000 |  | 7632.52 | -367.48
Painting | 5000 | 5000 | 3000 |  | 3244.51 | 244.51
Mechanicals
Heating \Air | 10000 | 7800 | 7800 |  | 6088.5 | -1711.5
Insulation | 2600 | 2600 | 1493 |  | 1493 | 0
Plumbing | 6700 | 6700 | 7200 |  | 7724.5 | 524.5
Electrical | 5000 | 5000 | 4500 |  | 4500 | 0
Interior
Drywall | 7000 | 7000 | 7700 |  | 7601.15 | -98.85
Flooring | 5000 | 5000 | 5000 |  | 2275.18 | -2724.82
Interior Finish work |  | 2000 | 3000 |  | 2940 | -60
Appliances\Cabinets\Fixtures | 5000 | 5000
Appliances |  |  | 300 |  | 212.06 | -87.94
Cabinets |  |  | 1600 |  | 1490.5 | -109.5
Fixtures |  |  | 2800 |  | 2922.22 | 122.22
Garage Repair | 3000 | 6000 | 6000 |  | 6389.01 | 389.01
Staircase |  | 3000 | 3328 |  | 3268.05 | -59.95
Porch \bay roof \shed |  | 2500 | 4500 |  | 4659.98 | 159.98
Basement door and windows |  | 1000 | 1000 |  | 538.95 | -461.05
Hauling |  | 800 | 1200 |  | 1344 | 144
Landscaping |  | 1000 | 1000 | 1000 |  | -1000
Miscellaneous costs |  |  | 1000 |  | 860.16 | -139.84
Tim-Bor pressure spray |  | 312 | 312 |  | 312 | 0
Taxes |  | 235 | 235 |  | 235 | 0
Utilities\hookup |  | 1000 | 2300 |  | 1977.52 | -322.48
General Contractor GRG | 8000 | 8000 | 2000 | 2000 |  | -2000
Hardware, trim, doors, etc ARS | 4000 | 4000 | 6425 |  | 6425 | 0
Selling Costs | 2100 | 2400 | 2700 | 2700 |  | -2700
Legal Fees | 1000 | 1000 | 1000 |  |  | -1000
Interest QC Housing Cluster Loan |  | 2400 | 3300 |  | 3210.8417 | -89.1583
Insurance |  | 600 | 800 |  | 800 | 0
Totals | 100400 | 129447 | 137072.74 | 5700 | 125725.0417 | -11347.6983
137072.74
131372.74