## Totals
730\732 Gaines Funding
Friends of Jipp | 2004-08-01 | 7555
Alcoa Credit Union | 2004-04-01 | 500
RDA Emergency Grant | 2004-08-01 | 2500
SHSI Emergency Grant | 2004-08-01 | 5500
RDA | 2005-05-01 | 35000
HSPG-1 | 2005-09-01 | 12000
HSPG-2 | 2005-12-14 | 9783.67
HSPG-3 | 2006-04-01 | 5597.96
HSPG-4 | 2008-01-02 | 3494.12
HSPG-5 | 2009-01-22 | 17109.48 | 47985.23
SCHC 1 | 2008-06-01 | 6000 | 99040.23
SCHC 2 | 1//1/2009 | 12000 | 100985.23
Total | as of March 2009 | 117040.23
730\732 Gaines Rehab Costs
Contractor |  | Cost
Phase 1 |  | 14629.12
Roof and gutters |  | 38349.55
Store floor and loading dock |  | 15602.96
Heating and cooling |  | 900
Electrical |  | 2627.5
Plumbing |  | 2178.41
Masonry |  | 7245.73
730 Flooring |  | 98.4
730 interior rehab |  | 41547.3493
Painting |  | 429.36
Misc |  | 1105.08
Utilities |  | 2871.78
Total | as of March 2009 | 127585.2393 | 28545.0093
Expenses owed
| jack | 1500.72
| marion | 212.52

## Roof
Roofing and gutters
Contractor | Date |  | Cost
Mark Construction Inv. 206 | 2005-08-26 | Cedar roof | 12000 | Req 1
Carvers Millworks Inv 1040 | 2005-08-27 | soffit trim | 700 | Req 2
Mark Construction Inv. 208 | 2005-09-14 | Cedar roof | 12000 | Req 1
Mark Construction Inv. 217 | 2005-11-07 | Cedar roof | 11870 | Req 3
Menards 26667 | 2006-03-26 | Down spouts | 19.95 | Req 4
B&B Sheet Metal downspouts Inv 16812 | 2006-11-15 | Down spouts | 675.6 | Req 4
Midwest sheet metal Invoice 1 | 2007-11-15 | install down spouts, loading dock gutter | 1084
Total | 2009-03-09 |  | 38349.55

## Store Flooring
Store flooring and loading Dock
Contractor | Date |  | Cost
Dan McDaniels Carpenter | 2005-08-04 | Dan McDaniels Carpenter | 108 | Req 2
Dan McDaniels helper | 2005-08-04 | Dan McDaniels helper | 48 | Req 2
Menards | 2005-08-17 | Store front | 475.16 | Req 2
Menards | 2005-10-03 | Store front | 85.42 | Req 2
Dan McDaniels Carpenter | 2005-10-04 | store front | 1500 | Req 2
MAGS | 2005-10-27 | front window | 19.26 | Req 2
Mark Construction Inv, 213 | 2005-10-11 | loading dock | 1183 | Req 2
Midwest Architectural Inv. | 2005-10-25 | store front windows | 958.72 | Req 2
Mark Construction Inv. 223 | 2005-12-20 | store floor | 10772 | Req 3
Menards 3994 | 2006-03-28 | ADA landing | 105.74 | Req 4
Menards 17366 | 2006-04-05 | Store front | 45.97 | Req 4
Menards 30631230607 | 2006-05-03 | store floor | 20.58 | Req 4
Menards 3981 06 9582 | 2006-07-26 | store floor | 22.18 | Req 4
Menards 70398 | 2006-06-13 | Ceiling joists | 52.26 | Req 4
Menards 14793 | 2006-06-17 | loading dock | 15.33 | Req 4
Menards 15225 | 2006-06-19 | Loading dock | 55.77 | Req 4
Menards 5482050541 | 2006-10-23 | store ceiling | 16.24 | Req 4
Menards 74721049651 | 2006-10-25 | store ceiling | 38.33 | Req 4
Dan McDanniels | 2006-10-27 | Dan McDanniels | 81 | Req 4
Total | 2009-03-09 |  | 15602.96

## Heating
Jipp Heating and cooling costs
Contractor | Date |  | Cost
Kale heating and cooling Inv. 16071-CR | 2007-10-04 | Store heating | 900 | Req 4
Kale heating and cooling Inv. 2420 | 2008-07-10 | Heating and Air Conditioning $6,385 on 730 costs |  | Req 5
McCormick Insulation Inv 4419 | 2008-08-18 | Insulation 730 $1582 on 730 costs |  | Req 5
Total | 2009-03-09 |  | 900

## Electrical
Jipp Electrical
Contractor | Date |  | Cost
Electricial Republic640814-00 | 2005-11-18 | Jipp store | 88.59 | req 3
Electricial Republic 640936-00 | 2005-11-18 | Jipp store | 75.62 | Req 3
Electricial Republic 646273-00 | 2005-12-16 | Jipp store | 14.2 | Req 3
Bruns Electric Inc. Inv 2910 | 2006-04-15 | Jipp store | 690.7 | req 4
Menards 84578 | 2006-06-16 | electrical supplies store | 242.08 | Req 4
Bruns Electric Inc. Inv 2945 | 2007-02-18 | Jipp Store | 628.41 | req 4
Bruns Electric Inc. Inv 2959 | 2007-06-17 | Jipp store | 887.9 | req 4
Bruns Electric Inc. Inv 3000 | 2008-10-01 | Jipp sub box for apt $1,252.85 on 730 costs |  | Req 5
Bruns Electric Inc. Inv 3009 | 2008-11-16 | 730 rough in wiring $682.41 on 730 costs |  | Req 5
Total | 2009-03-09 |  | 2627.5

## Plumbing
730¦732 Plumbing
Contractor | Date |  | Cost
Ewert Plumbing 7/17/07 | 2007-07-17 | Store plumbing | 2178.41
JMC\Ewert | 2008-09-01 | Apartment Plumbing $3,151.53 on 730 costs
Complete plumbing $1,748.28 on 730 costs
Ewert |  | Basement drain
Total | 2009-03-09 |  | 2178.41

## Masonry
Jipp Masonry work
Contractor | Date |  | Cost
Delveau Construction Inv 275381 | 2005-09-04 | Rebuild house chimney | 1610 | Req 2
Roger Cole | 2005-10-01 | Store front wall | 380 | Req 2
Builders Sand and Gravel 59155 | 2005-10-19 | Store front wall | 29.78 | Req 2
Andrew Masonary | 2005-10-20 | repair north store wall | 600 | Req 2
Tom Stoffers back wall | 2008-10-21 | rear wall 730 | 4000 | Req 5
door ways | 2008-10-21 | doorway between 730-732 | 460 | Req 5
Builders sand & cement 72421 | 2008-08-28 | rear wall motar | 61.23 | Req 5
Quint City Stone JA-17339 | 2008-08-28 | rear wall footing | 69.56 | Req 5
Lowes S0107LS1 141544 | 2008-09-03 | rear wall tools | 35.16 | Req 5
Tom Stoffers cellar wall
Total | 2009-03-09 |  | 7245.73

## 730 Flooring
Jipp Flooring
Contractor | Date |  | Cost
Menards 20942053753 | 2008-04-04 | Flooring back room | 98.4 | Req 5
Menards 306316608075983 | 2008-06-14 | flooring apartment $1,137.30 on 730 costs |  | Req 5
Menards 93296 07 4241 | 2008-12-14 | underlayment apartment $151.28 on 730 costs |  | Req 5
Total | 2009-03-09 |  | 98.4

## 730 Rehab
730 Apartment Rehab
Contractor | Date |  | Cost
JMC Remodeling | 2008-06-10 | layout, rebuild 2nd floor Kitchen, | 3000 | Req 5
|  | Bathroom, Bedroom | 3308 | Req 5
|  | Rebuild north wall, clean out first floor | 2562.38 | Req 5
| 2008-09-01 | Drywall | 3433.53 | Req 5
|  | JMC Total | 12303.91
Menards 306322608083644 | 2008-08-13 | nails studs | 150.6 | Req 5
Menards 306322708059164 | 2008-08-14 | studs, plywood | 80.59 | Req 5
Menards 306322908077437 | 2008-08-16 | studs | 103.51 | Req 5
Menards 306323108068967 | 2008-08-18 | studs | 23.22 | Req 5
Finish first floor
Menards 73086068052 | 2009-02-17 | Sheetrock front parlour | 253.68 | Jack
Menards 78553025256 | 2009-02-23 | Sheetrock back room \misc | 92.3 | Jack
Menards 32962074196 | 2009-03-05 | Sheetrock back room \misc | 84.17 | Jack
Menards 11511056508 | 2009-03-06 | Sheetrock back room \misc | 65.76 | Jack
Menards 84721057425 | 2009-03-09 | Sheetrock back room \sockets\misc | 29.92 | Jack
Lighting
Menards 39435045122 | 2009-02-26 | Lighting for apartment | 221.77 | coupon
Flicks 000011 | 2009-03-09 | Exterior lights | 80.44 | Jack
Menards 15844015065 | 2009-03-13 | Kitchen lights | 110.95 | Jack
Kitchen
Home Depot 2110000569418 | 2009-03-15 | Counter\sink | 172.26 | Jack
Bathroom
Menards 22658078547 | 2009-03-15 | Durock\denshield\misc | 146.15 | Jack
Lowes S0107CA1 1334553 | 2009-03-18 | floor and shower Tile | 213.44 | Jack
Total | 2009-03-09 |  | 14132.67
|  | Jack | 1249.07

## Painting
Painting
Contractor | Date |  |  | Cost
Keims exterior painting Inv A36134 | 2005-09-24 | paint store |  | 117.57 | Req 3
Lowes store paint 14416 | 2006-06-02 | Paint store |  | 71.99 | Req 4
Keims exterior painting Inv A23906 | 2006-09-13 | paint store |  | 239.8 | Req 4
Sherwin-Williams 2063-4 | 2008-08-25 | paint 730 | 31.74 |  | Req 5
Sherwin-Williams 6447-5 | 2008-12-06 | paint 730 | 50.16 |  | Req 5
Sherwin-Williams 6639-7 | 2008-12-12 | paint 730 | 50.16 |  | Req 5
Sherwin-Williams 6494-2 | 2008-12-13 | paint 730 | 87.89 |  | Req 5
Home Depot 21110005870506 | 2008-12-16 | paint 730 | 22.41 |  | marion
Menards 15225055940 | 2009-01-07 | paint 730 | 22.18 |  | marion
Menards 15225076529 | 2009-01-18 | paint 730 | 36.31 |  | marion
Menards 20942078897 | 2009-01-24 | paint 730 | 24.2 |  | marion
Menards 48441069592 | 2009-01-30 | paint 730 | 49.15 |  | marion
Menards 22658062988 | 2009-02-06 | paint 730 | 29.91 |  | marion
Menards 48441083414 | 2009-02-08 | paint supplies 730 | 4.93 |  | marion
Home Depot 21110005807599 | 2009-02-16 | paint supplies 730 | 17.43 |  | marion
Menards 90021037956 | 2009-03-09 | paint supplies 730 | 14.59 |  | jack
Total | 2009-03-09 |  |  | 429.36
|  | Jack |  | 14.59
|  | Marion |  | 206.52

## Misc
730\732 Miscellaneous Costs
Contractor | Date |  | Cost
Mags glass 600243 | 2005-11-08 | safety glass front store window | 47.08 | Req 3
Menards 46184 | 2006-01-20 |  | 80.85 | Req 3
Menards 84630056886 Jipp Misc | 2007-04-20 | felt\tools | 37.35 | chk 1601
Menards 73088059573 Jipp Misc | 2007-05-18 | Hardware | 55.34 | chk 1601
Home Depot 21110005755442 Jipp Misc | 2007-05-18 | locks | 9.08 | chk 1601
Kmart 0935909070802612111 | 2008-09-07 | toilet seat Jipp bathroom | 16.04 | Req 5
Home Depot 21110001099373 | 2008-08-26 | saw blades framing | 29.91 | Req 5
Menards 306323108068965 | 2008-08-18 | bathroom fan, Jipp water heater | 326.51 | Req 5
Menards 306323208086463 | 2008-08-19 | Jipp bathroom | 41.03 | Req 5
True Value JRNL#I52057 | 2008-08-20 | Jipp bathroom | 13.88 | Req 5
Menards 306324108073129 | 2008-08-28 | Jipp | 64.5 | Req 5
Menards 306325308059564 | 2008-09-09 | Mason blades rear wall | 24.75 | Req 5
Menards 26920049397 | 2009-02-10 | Baseboard trim | 128.11 | jack
Pittsburgh Paints 000024369 | 2009-02-16 | Window putty (Allan Hayes) | 6 | marion
Acetool 50389 | 2009-02-23 | Router bit base board ogee | 115.7 | jack
Menards 20942062242 | 2009-02-25 | Misc paint\screws | 33.5 | jack
Menards 15844026094 | 2009-02-28 | Front door lock\painting\misc | 75.45 | jack
Total | 2009-03-09 |  | 1105.08
|  | Jack | 237.06
|  | Marion | 6

## Utilities
730\732 Utilities
Contractor | Date |  | Cost
MidAmerican | 2007-12-20 | Electric\gas | 262.55
MidAmerican | 2008-01-25 | Electric\gas | 320.45
MidAmerican | 2008-02-22 | Electric\gas | 342.23
MidAmerican | 2009-03-24 | Electric\gas | 277.78
MidAmerican | 2008-04-22 | Electric\gas | 100.74
MidAmerican | 2008-05-21 | Electric\gas | 31.63
MidAmerican | 2008-06-20 | Electric\gas | 32.68
MidAmerican | 2008-07-22 | Electric\gas | 30.03
MidAmerican | 2008-08-20 | Electric\gas | 42.21
MidAmerican | 2008-09-19 | Electric\gas | 121.15
MidAmerican | 2008-10-24 | Electric\gas | 38.21
MidAmerican | 11//2008 | Electric\gas | 114.93 | 1714.59 | 2008
MidAmerican | 12//2008 | Electric\gas | 503.23
MidAmerican | 2009-01-27 | Electric\gas | 415.37
MidAmerican | 2009-02-26 | Electric\gas | 238.59 | 1157.19 | 2009
Total | 2009-03-09 |  | 2871.78

## HSPG 1 - 2
Request 1
2005-08-26 | 206 | Mark Construction Inv. 206 | Cedar Roof | 12000
2005-09-14 | 208 | Mark Construction Inv. 208 | Cedar roof | 12000
|  |  | Total | 24000
Request 2
DATE | INVOICE # | Cash Match | Expenditures from Grant | Total
|  | (What is being paid with | (What is being paid with
|  | your portion?) | grant funds?)
|  | Name of Vendor | Name of Vendor
2005-08-04 |  | $54 Dan McDaniels Carpenter | $54 Dan McDaniels Carpenter | 108
2005-08-04 |  | $24 Dan McDaniels helper | $24 Dan McDaniels helper | 48
2005-08-17 |  | $237.58 Menards | $237.58 Menards | 475.16 | 631.16
2005-08-27 | 1040 | $350 Carvers Millworks | $350 Carvers Millworks | 700
2005-09-04 | 275381 | $805 Delveau Construction | $805 Delveau Construction | 1610
2005-10-01 |  | $190 Roger Cole Mason | $190 Roger Cole Mason | 380
2005-10-03 |  | $42.71 Menards | $42.71 Menards | 85.42
2005-10-04 |  | $750 Dan McDaniels Carpenter | $750 Dan McDaniels Carpenter | 1500
2005-10-11 | 213 | $591.50 Mark Construction | $591.50 Mark Construction | 1183
2005-10-19 | 59155 | $14.89 Builders S & C | $14.89 Builders S & C | 29.78
2005-10-20 |  | $300 Andrews Masonry | $300 Andrews Masonry | 600
2005-10-25 | Invoice | $479.36 Midwest Architectural | $479.36 Midwest Architectural | 958.72
2005-10-27 | 600234 | $9.63 MAGS | $9.63 MAGS | 19.26
2005-11-07 | 217 | $5,935 Mark Construction | $5,935 Mark Construction | 11870
| TOTAL | 9783.67 | 9783.67 | 19567.34
49150
Reguest 1 | 12000
Remaining | 37150
Request 2 | 9783.67
Remaining | 27366.33

## HSPG 3
Request 3
DATE | INVOICE # | Cash Match | Expenditures from Grant | Total
|  | (What is being paid with | (What is being paid with
|  | your portion?) | grant funds?)
|  | Name of Vendor | Name of Vendor
2005-09-24 | A36134 | $58.79 paint Keim's Paint Center | $58.79 paint Keim's Paint Center | 117.57
2005-11-08 | 600243 | $23.54 MAGS glass | $23.54 MAGS glass | 47.08
2005-11-18 | 640814-00 | $44.30 Electricial Republic | $44.30 Electricial Republic | 88.59
2005-11-18 | 640936-00 | $37.81 Electricial Republic | $37.81 Electricial Republic | 75.62
2005-12-16 | 646273-00 | $7.10 Electricial Republic | $7.10 Electricial Republic | 14.2
2005-12-20 | 223 | $5,386 Mark Construction | $5386 Mark Construction | 10772
2006-01-20 | 46184 | $40.48 Menards | $40.48 Menards | 80.85
| TOTAL | 5597.955 | 5597.955 | 11195.91
49150
Reguest 1 | 12000
Remaining | 37150
Request 2 | 9783.67
Remaining | 27366.33
Request 3 | 5597.955
Remaining | 21768.375

## HSPG 4
Request 4
Request 4
| DATE | INVOICE # |  | Cash Match |  | Expenditures from Grant | Total
|  |  |  | (What is being paid with |  | (What is being paid with
|  |  |  | your portion?) |  | grant funds?)
|  |  |  | Name of Vendor |  | Name of Vendor
1 | 2006-03-26 | 26667 | 9.975 | Menards Down spout | 9.975 | Menards Down spout | 19.95
2 | 2006-03-28 | 3994 | 52.87 | Menards ADA landing | 52.87 | Menards ADA landing | 105.74
3 | 2006-04-05 | 17366 | 22.985 | Menards Store front | 22.985 | Menards Store front | 45.97
4 | 2006-05-03 | 30631230607 | 10.29 | Menards store floor | 10.29 | Menards store floor | 20.58
5 | 2006-06-02 | 14416 | 35.995 | Lowes store paint | 35.995 | Lowes store | 71.99
6 | 2006-07-26 | 3981 06 9582 | 11.09 | Menards store floor | 11.09 | Menards store floor | 22.18
7 | 2006-06-13 | 70398 | 26.13 | Menards Ceiling joists | 26.13 | Menards Ceiling joists | 52.26
8 | 2006-06-16 | 84578 | 121.04 | Menards Electrical | 121.04 | Menards Electrical | 242.08
9 | 2006-06-17 | 14793 | 7.665 | Menards loading dock | 7.665 | Menards loading dock | 15.33
10 | 2006-06-19 | 15225 | 27.885 | Menards Loading dock | 27.885 | Menards Loading dock | 55.77
11 | 2006-09-13 | A23906 | 119.9 | Keims exterior painting | 119.9 | Keims exterior painting | 239.8
12 | 2006-10-23 | 5482050541 | 8.12 | Menards store ceiling | 8.12 | Menards store ceiling | 16.24
13 | 2006-10-25 | 74721049651 | 19.165 | Menards store ceiling | 19.165 | Menards store ceiling | 38.33
14 | 2006-04-15 | 2910 | 345.35 | Burns Electric | 345.35 | Bruns Electric | 690.7
15 | 2007-02-18 | 2945 | 314.205 | Burns Electric | 314.205 | Bruns Electric | 628.41
16 | 2007-06-17 | 2959 | 443.95 | Burns Electric | 443.95 | Bruns Electric | 887.9
17 | 2007-07-17 | 07-158 | 1089.205 | Ewert Plumbing | 1089.205 | Ewert Plumbing | 2178.41
18 | 2006-11-15 | 16812 | 337.8 | B&B Sheet Metal downspouts | 337.8 | B&B Sheet Metal downspouts | 675.6
19 | 2007-10-04 | 16071-CR | 450 | Kale Heating | 450 | Kale Heating | 900
20 | 2006-10-27 |  | 40.5 | Dan McDanniels | 40.5 | Dan McDanniels | 81
|  |  |  | 3494.12 |  | 3494.12 | 6988.24
49150
| Reguest 1 | 12000
| Remaining | 37150 |  |  |  | Amount spent to date
| Request 2 | 9783.67 |  |  |  | 30875.75
| Remaining | 27366.33
| Request 3 | 5597.96
| Remaining | 21768.37
| Request 4 | 3494.12
| Remaining | 18274.25

## HSPG 5
| HSPG Request 5 |  |  |  |  | 2009-08-13 17:11
| DATE | INVOICE # |  | Cash Match |  | Expenditures from Grant | Total
|  |  |  | Name of Vendor |  | Name of Vendor
1 | 2008-11-01 | JMC remolding | 8601.64 | JMC Remodeling | 8601.64 | JMC Remodeling | 17203.28
2 | 2008-12-17 | 22420 | 3192.5 | Kale Company | 3192.5 | Kale Company | 6385
3 | 2008-10-01 | 3000 | 626.425 | Bruns Electric Inc. | 626.425 | Bruns Electric Inc. | 1252.85
4 | 2008-11-16 | 3009 | 341.205 | Bruns Electric Inc. | 341.205 | Bruns Electric Inc. | 682.41
5 | 2008-10-10 | 4419 | 791 | McCormick | 791 | McCormick | 1582
6 | 2008-10-21 | Statement | 2230 | Stoffers Property | 2230 | Stoffers Property | 4460
7 | 2008-08-28 | 72421 | 30.615 | Builders S & G | 30.615 | Builders S & G | 61.23
8 | 2008-09-23 | 141544 | 17.58 | Lowes | 17.58 | Lowes | 35.16
9 | 2008-08-28 | JA-17339 | 34.78 | Quint City Stone | 34.78 | Quint City Stone | 69.56
10 | 2008-04-04 | 20942053753 | 49.2 | Menards | 49.2 | Menards | 98.4
11 | 2008-06-14 | 20942075983 | 568.65 | Menards | 568.65 | Menards | 1137.3
12 | 2008-12-14 | 93296074241 | 78.64 | Menards | 78.64 | Menards | 157.28
13 | 2008-08-13 | 306322608083644 | 75.3 | Menards | 75.3 | Menards | 150.6
14 | 2008-08-14 | 306322708059164 | 40.295 | Menards | 40.295 | Menards | 80.59
15 | 2008-08-16 | 306322908077437 | 51.755 | Menards | 51.755 | Menards | 103.51
16 | 2008-08-18 | 306323108068967 | 11.61 | Menards | 11.61 | Menards | 23.22
17 | 2008-08-25 | 2063-4 | 15.87 | Sherwin-Williams | 15.87 | Sherwin-Williams | 31.74
18 | 2008-12-06 | 6447-5 | 25.08 | Sherwin-Williams | 25.08 | Sherwin-Williams | 50.16
19 | 2008-12-12 | 6639-7 | 25.08 | Sherwin-Williams | 25.08 | Sherwin-Williams | 50.16
20 | 2008-12-13 | 6494-2 | 43.945 | Sherwin-Williams | 43.945 | Sherwin-Williams | 87.89
21 | 2008-08-26 | 21110001099373 | 14.955 | Home Depot | 14.955 | Home Depot | 29.91
22 | 2008-08-18 | 306323108068965 | 163.255 | Menards | 163.255 | Menards | 326.51
23 | 2008-08-19 | 306323208086463 | 20.515 | Menards | 20.515 | Menards | 41.03
24 | 2008-08-20 | JRNL#I52057 | 6.94 | True Value | 6.94 | True Value | 13.88
25 | 2008-08-28 | 306324108073129 | 32.25 | Menards | 32.25 | Menards | 64.5
26 | 2008-09-07 | 9.3591e+17 | 8.02 | Kmart | 8.02 | Kmart | 16.04
27 | 2008-09-09 | 306325308059564 | 12.375 | Menards | 12.375 | Menards | 24.75
|  |  |  | 17109.48 |  | 17109.48 | 34218.96
49150
| Reguest 1 | 12000
| Remaining | 37150 |  |  |  | Amount spent to date
| Request 2 | 9783.67 |  |  |  | 95970.46
| Remaining | 27366.33
| Request 3 | 5597.96
| Remaining | 21768.37
| Request 4 | 3494.12
| Remaining | 18274.25
| Request 5 | 17109.48
1164.77

## Jipp phase1
Friends of Jipp Project November 30, 2004
| Donations | 7505
| Alcoa Employees and Community Credit Union | 500
| RDA Emergency Grant | 2500
| SHSI Emergency Grant | 5500
| Total | 16005
Expenses
| Tan Architect |  | 500
| VonMaur Construction |  | 6795
| Seiffert Lumber September |  | 1344.32
| Seiffert Lumber October |  | 882.36
| Mark Construction |  | 1278.5
| GRG Expenses |  | 3828.94
| Total Expenses |  | 14629.12
Jipp Project Gateway Redevelopment Group Expenses
Date | Description | Amount |  |  | Status
|  | Framing\Roofing | Misc | Phase 2
2004-06-04 | Menards-tarps |  | 39.63 |  | Paid
2004-06-07 | Menards-tarps |  | 41.3 |  | Paid
2004-09-01 | USPS Emergency grant |  | 13.65 |  | Paid
2004-09-11 | USPS Emergency grant |  | 13.65 |  | Paid
2004-09-13 | USPS-HSPG |  | 27.3 |  | Paid
2004-09-15 | Menards-metal valley |  | 9.21 |  | Paid
2004-09-16 | Kinko's |  | 7.03 |  | Paid
2004-09-17 | Architect-travel expenses |  | 65 |  | Paid
2004-09-24 | Menards-Mobile home Jacks | 54.47 |  |  | Paid
2004-10-03 | Menards-hardware | 39.11 |  |  | Paid
2004-10-06 | Menards-lumber | 59.15 |  |  | Paid
2004-10-07 | Menards-lumber | 10.58 |  |  | Paid
2004-10-13 | Midwest Architectural deposit |  |  | 500 | Paid
2004-10-19 | Builders Sand and Gravel |  |  | 36.89 | Paid
2004-10-20 | Builders Sand and Gravel |  |  | 5.4 | Paid
2004-10-11 | City of Davenport Building permit |  | 35.75 |  | Paid
2004-10-25 | Menards-lumber | 56.22 |  |  | Paid
2004-10-25 | Roger Cole mason |  |  | 650 | Paid
2004-10-27 | Menards-hardware | 37.17 |  |  | Paid
2004-10-30 | Menards-lumber | 58.72 |  |  | Paid
2004-11-01 | Menards-lumber, tarps | 97.06 |  |  | Paid
2004-11-10 | Menards-lumber | 108.86 |  |  | Paid
2004-11-13 | Menards-lumber\roofing | 202.06 |  |  | Paid
2004-11-17 | Menards-Lumber\ roofing | 349.49 |  |  | Paid
2004-11-17 | Kinko's |  | 16.59 |  | Paid
2004-11-18 | Menards-Lumber\ roofing | 118.57 |  |  | Paid
2004-11-19 | Menards-Lumber\ roofing | 199.37 |  |  | Paid
2004-11-21 | Menards-Lumber\roofing, Bill | 46.22 |  |  | Paid
2004-11-22 | Menards-Lumber\roofing | 97.89 |  |  | Paid
2004-11-22 | Menards-Lumber\roofing | 32.6 |  |  | Paid
2004-11-01 | Architect for grant |  | 500 |  | Paid by SHSI
2004-11-10 | First Dumster |  | 300 |  | Paid
| Totals | 1567.54 | 1069.11 | 1192.29
Total GRG Expenses |  | 3828.94
Jipp Project Costs\Estimates
|  | Estimate | Phase 2 Est. | Actual | Net
Foundation |  | 7000 |  | 6795 | 205
Lumber |  | 3000 |  | 3794.22 | -794.22
Phase 2 now | 3 - 4' x 10' Store window sashes |  | 1412 | 500 | 912
| Store front brick corner column |  | 900 | 692.29 | 207.71
| Store front window framing |  | 200 |  | 200
Misc |  |  |  | 1069.11 | -1069.11
Architect | for State grants |  |  | 500 | -500
Framer | needed to complete roof |  |  | 1278 | -1278
| Original Estimate | 10000
| Phase 2 addition |  | 2512
| Needed extras |  |  | 2847.11
| Total Estimate Costs |  | 12512
| Total Actual Spent as of | 2009-08-13 17:11 |  | 14628.62 | -2116.62
| Phase 1 actual total cost |  |  | 12936.33
Total Updated Project Cost Estimate |  |  | 15740.62

## g march debts
Jack's unpaid GRG expenses
Date | Item | Amount | Paid | Check
2007-02-22 | 822 Loan | 5000 | 2009-03-01 | 1599
| 822 charges 2006-2008 | 16500.98
| HSPG Request 4 | 1621.82 | 2009-03-01 | 1602
| HSPG Request 5 | 2417.43 | 2009-03-01 | 1603
2006-06-19 | Davenport sewer 730 Gaines | 48.5 |  | 1601
2006-09-25 | Davenport sewer 730 Gaines | 62.25 |  | 1601
2007-03-04 | Davenport sewer 730 Gaines | 43.11 |  | 1601
2007-02-07 | QuickBooks | 259.99 |  | 1601
2006-02-28 | MS Front page web site | 78 |  | 1601
2006-08-31 | Godaddy website | 43.09 |  | 1601
2007-04-20 | Menards 84630056886 Jipp Misc | 37.35 |  | 1601
2007-05-18 | Menards 73088059573 Jipp Misc | 55.34 |  | 1601
2007-05-18 | Home Depot 21110005755442 Jipp Misc | 9.08 |  | 1601
2008-06-21 | Office Max 36440556 ink | 53.49 |  | 1601
| EBay sales shipping 2006-2008 | 120.7 | 2009-03-01 | 1601
810.9
Total |  | 16500.98
Marion's unpaid expenses
Date | Item | Amount | Paid | Check
| 822 Charges | 3024.42 | 2009-03-01 | 1600
| HSPG Request 5 | 235.99 | 2009-03-01 | 1604
2008-12-16 | Home Depot 21110005870506 Jipp Apt. painting | 22.41
2009-01-07 | Menards 15225055940 Jipp Apt. painting | 22.18
2009-01-18 | Menards 15225076529 Jipp Apt. painting | 36.31
2009-01-24 | Menards 20942078897 Jipp Apt. painting | 24.2
2009-01-30 | Menards 48441069592 Jipp Apt. painting | 49.15
Total |  | 154.25
Contractors unpaid expenses
Date | Item | Amount | Paid | Check
2008-07-10 | Kale Jipp apartment | 6385 | 2009-02-16 | 1596
2008-11-16 | Bruns Jipp apartment | 1935.26 | 2009-02-16 | 1597
2008-08-18 | McCormick Insulation | 1582 | 2009-02-16 | 1598
| JMC completed plumbing | 1748.28 | 2009-03-01 | 1605
| Scott County Landfill | 594
2008-08-25 | IA- IL Termite&Pest (chk 1576 not cleared) | 312 | 2009-02-16 | 1595
Total |  | 594
| Total GRG debts | 17249.23 | 2009-03-01

## 730 Apt
730 Gaines Rehab Costs |  |  |  |  | July 27,2009
Contractor | Date |  | Cost | Jipp costs | Paid by | Date | sub totals
JMC Remodeling |  | layout, rebuild 2nd floor Kitchen, | 3000 |  | GRG 1559 | 2008-06-11
|  | Bathroom, Bedroom | 3308 |  | GRG 1563 | 2008-07-11
|  | Rebuild north wall, gut first floor | 2562.38 |  | GRG 1587 | 2008-09-03
|  | Plumbing | 3151.53 |  | GRG 1588 | 2008-09-17
|  | Drywall | 3433.53 |  | GRG 1593 | 2008-11-03
|  | Cmplete plumbimg | 1748.28 |  | GRG 1605 | 2009-03-01
17203.72
Kale heating and cooling | 2008-07-10 | Heating and Air Conditioning | 6385 |  | GRG 1596 | 2009-02-16
6385
Bruns Electric | 2008-11-16 | Completely rewire 730 | 1935.26 |  | GRG 1597 | 2009-02-16
| 2009-05-03 | Materials-Electrical | 216.44 |  | GRG 1610
2151.7
McCormick Insulation | 2008-08-18 | Insulation 730 | 1582 |  | GRG 1598 | 2009-02-16
1582
Brick work
Builders sand & cement | 2008-08-28 |  | 61.23 |  | JH | 2009-03-01 | GRG 1603
Quint City Stone | 2008-08-28 | Back wall limestone | 69.56 |  | JH | 2009-03-01 | GRG 1603
Lowes S0107LS1 141544 | 2008-09-03 |  | 35.16 |  | JH | 2009-03-01 | GRG 1603
Tom Stoffers back wall | 2008-10-21 | rear wall 730 | 4000 |  | GRG 1591 | 2008-09-18
door ways | 2008-10-21 | doorway between 730-732 | 460 |  | GRG 1592 | 2008-09-18
4625.95
Flooring
Menards 20942053753 | 2008-04-04 | back room flooring | 98.4 |  | JH | 2009-03-01 | GRG 1603
Menards 306316608075983 | 2008-06-14 | flooring | 1137.3 |  | JH | 2009-03-01 | GRG 1603
Menards 93296 07 4241 | 2008-12-14 | underlayment | 157.28 |  | JH | 2009-03-01 | GRG 1603
1392.98
Framing material
Menards 306322608083644 | 2008-08-13 | nails studs | 150.6 |  | JH | 2009-03-01 | GRG 1603
Menards 306322708059164 | 2008-08-14 | studs, plywood | 80.59 |  | JH | 2009-03-01 | GRG 1603
Menards 306322908077437 | 2008-08-16 | studs | 103.51 |  | JH | 2009-03-01 | GRG 1603
Menards 306323108068967 | 2008-08-18 | studs | 23.22 |  | JH | 2009-03-01 | GRG 1603
357.92
Painting
Sherwin-Williams 2063-4 | 2008-08-25 | paint | 31.74 |  | MM | 2009-03-01 | GRG 1604
Sherwin-Williams 6447-5 | 2008-12-06 | paint | 50.16 |  | MM | 2009-03-01 | GRG 1604
Sherwin-Williams 6639-7 | 2008-12-12 | paint | 50.16 |  | MM | 2009-03-01 | GRG 1604
Sherwin-Williams 6639-7 | 2008-12-12 | paint | 50.16 |  | MM | 2009-03-01 | GRG 1604
Sherwin-Williams 6494-2 | 2008-12-13 | paint | 87.89 |  | MM | 2009-03-01 | GRG 1604
Home Depot 21110005870506 | 2008-12-16 | Misc sandpaper | 22.41 |  | MM
Menards 15225055940 | 2009-01-07 | Misc painting | 22.18 |  | MM
Menards 15225076529 | 2009-01-18 | Misc painting | 36.31 |  | MM
Menards 20942078897 | 2009-01-24 | Misc painting | 24.2 |  | MM
Menards 48441069592 | 2009-01-30 | Misc painting | 49.15 |  | MM
Menards 22685062988 | 2009-02-06 | Misc painting | 29.91 |  | MM
Menards 48441083414 | 2009-02-08 | paint supplies | 5.03 |  | MM
Home Depot 21110005807599 | 2009-02-16 | paint supplies | 17.43 |  | MM
Pittsburgh Paints 000024369 | 2009-02-16 | Window putty (Allan Hayes) | 6 |  | MM
Menards 90021037956 | 2009-03-09 | Painting | 14.59 |  | JH
Sherwin Williams | 2009-03-11 | Paint | 31.49 |  | MM
Menards 78553063906 | 2009-03-12 | wall size | 12.83 |  | MM
Lowes S0107JC2 1467 | 2009-04-29 | Paint Supplies | 45.42 |  | MM
Diamond Vogel | 2009-05-01 | Paint | 315.52 |  | MM
Menards 57448 04 1334 | 2009-05-01 | paint supplies | 21.23 |  | JH
Stripping Solution | 2009-05-01 | Spindle stripping | 5 |  | JH
928.81
Finish first floor
Menards 73086068052 | 2009-02-17 | Sheetrock front parlour | 253.68 |  | JH
Menards 78553025256 | 2009-02-23 | Sheetrock back room \misc | 92.3 |  | JH
Menards 32962074196 | 2009-03-05 | Sheetrock back room \misc | 84.17 |  | JH
Menards 11511056508 | 2009-03-06 | Sheetrock back room \misc | 65.76 |  | JH
495.91
Kitchen
Home Depot 21110569418 | 2009-03-15 | Kitchen counter and sink | 172.26 |  | JH
Home Depot 48118393041 | 2009-04-18 | Endcap Kit-Counter | 13.91 |  | JH
Lowes Online receipt | 2009-06-22 | Stove & Refrigerator | 1033.62 |  | JH
Lowes S0107AK2 1027000 | 2009-06-28 | Electrical Cord for Range | 21.36 |  | JH
Menards 11511 08 4024 | 2009-07-04 | Light Bulbs and wall base adhesive | 38.49 |  | JH
1279.64
Bathroom
Menards 22658078547 | 2009-03-15 | Bathroom floor misc | 146.15 |  | JH
Lowes S0107ca11334553 | 2009-03-18 | Bathroom tile | 213.44 |  | JH
Menards 5853006307 | 2009-04-10 | Misc bathroom & varnish | 31.23 |  | JH
Menards 84712064977 | 2009-04-14 | Trim boards and mortar | 31 |  | JH
Flick MC 85138503DS66D8YKT | 2009-04-18 | Bathroom Sink and Faucet | 166.24 |  | JH
Home Depot 010306760003 | 2009-04-21 | Grout and Grout Bag | 18.05 |  | JH
Menards 44806600127 | 2009-06-08 | Thinset | 18.86 |  | JH
Home Depot 211100003 38970 | 2009-06-08 | Grout & Bulbs | 24.45 |  | JH
Menards 46125 04 3179 | 2009-06-18 | Toilet ,Seat & Back misc | 107.75 |  | JH
Home Depot 2111 00003 05722 | 2009-07-07 | Medicine Cabinet and ? | 143.35 |  | JH
Home Depot 2111 00003 05748 | 2009-07-07 | Silicone | 6.39 |  | JH
Home Depot 2111 00012 58912 | 2009-07-06 | Thinset | 18.18 |  | JH
Lowes S0107CC1 141539 | 2009-07-06 | Tile | 33.29 |  | JH
Big Lots 5381 | 2009-07-18 | Towel Bars | 20.33 |  | MM
Menards 46090 03 9914 | 2009-07-19 | Paper Holder | 10.6893 |  | MM
989.3993
Lighting
Menards 39435045122 | 2009-02-26 | Lighting for apartment | 221.77 |  | GRG
Menards 39435045122 | 2009-02-26 | Lighting for apartment | 1.27 |  | MM
Flicks 000011 | 2009-03-09 | Lighting for apartment | 80.44 |  | JH
Menards 15844015065 | 2009-03-13 | Lighting for apartment | 110.95 |  | JH
414.43
Misc
Kmart 0935909070802612111 | 2008-09-07 | toilet seat Jipp bathroom |  | 16.04 | MM | 2009-03-01 | GRG 1604
Home Depot 21110001099373 | 2008-08-26 | saw blades framing |  | 29.91 | JH | 2009-03-01 | GRG 1603
Menards 306323108068965 | 2008-08-18 | bathroom fan, Jipp water heater | 326.51 | 326.51 | JH | 2009-03-01 | GRG 1603
Menards 306323208086463 | 2008-08-19 | Jipp bathroom |  | 41.03 | JH | 2009-03-01 | GRG 1603
True Value JRNL#I52057 | 2008-08-20 | Jipp bathroom |  | 13.88 | JH | 2009-03-01 | GRG 1603
Menards 306324108073129 | 2008-08-28 | Jipp |  | 64.5 | JH | 2009-03-01 | GRG 1603
Menards 306325308059564 | 2008-09-09 | Mason blades rear wall | 24.75 |  | JH | 2009-03-01 | GRG 1603
Restore | 2009-02-06 | Misc insulation | 13.2 |  | JH
Menards 26920049397 | 2009-02-10 | Baseboard trim | 128.11 |  | JH
Ace Tool 50389 | 2009-02-23 | Molding bit | 115.7 |  | JH
Menards 20942062242 | 2009-02-25 | Misc paint\screws | 33.5 |  | JH
Menards 15844026094 | 2009-02-28 | Front door lock\painting\misc | 75.45 |  | JH
Menards 84721057425 | 2009-03-09 | Misc | 29.92 |  | JH
SOI MCVISA1 | 2009-03-18 | Certificate of good standing |  | 5 | JH
Home Depot 21110005777016 | 2009-04-02 | Misc tools | 7.03 |  | JH
Menards 12476061482 | 2009-04-07 | misc | 26.28 |  | JH
Menards 17366056568 | 2009-04-23 | Wood | 17.14 |  | JH
Scott Area Landfill | 2009-04-24 | Trash Dump | 25 |  | JH
Menards 32976067576 | 2009-05-05 | Wood Trim- | 115.97 |  | JH
MLCS Woodworking | 2009-05-11 | Router bits for apartment baseboard | 69 |  | JH
Office Max | 2009-05-15 | Ink & Paper for printer |  | 144.65 | MM
Stetson Building Do5712 | 2009-05-29 | Lime Bag |  | 4.45 | JH
Builders 78529968 | 2009-05-29 | Bag of Portland |  | 20.13 | JH
Tom Stoffers Masonry 137253 | 2009-05-29 | Repair of Basement Wall |  | 800 | GRG 1609
Menards 46099 06 5826 | 2009-06-08 | Misc | 8.26 |  | JH
Menards 71 03 7563 | 2009-07-06 | Molding and Electrical Covers | 73.72 |  | JH
K&K | 2009-07-11 | Saw Blades | 21.92 |  | JH
Lowes S0107SV2 1295356 | 2009-07-11 | Brads and 24 x 24 inch square | 40.47 |  | JH
Speedysigns.com | 2009-07-15 | house numbers | 28.68 |  | GRG PP
Menards 73088088648 | 2009-07-16 | Dryer vent, misc | 76.63 |  | JH
Restore | 2009-07-16 | flooring | 6.5 |  | JH
Menards 46119 05 1302 | 2009-07-24 | Molding, closet shelving, Misc. | 176.15 |  | JH
Midwest Architectural | 2009-07-27 | Storm and screen windows | 2300 |  | GRG
|  |  |  | 1466.1 |  |  | 3739.89
Total |  |  | 41547.3493 |  |  |  | 41547.3493
| JH | 4050.67
| MM | 650.1693
| GRG | 36871.09
41571.9293